## NCCA
Identified On | Non-Conformity | Cause Analysis | Owner | Corrective Actions Taken | Last Updated | Status | Review Results
2024-10-14 | Documents missing critical details. | Lack of communication, lack of collaboration. | CEO - Aaron COO - Merlyn CSO - Gaurav CFO - Niranjan Dev CRO - Hemanth | Completed required details. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | Detailed, but processes are not explained & lack of documentation. | Lack of clarity in direction. Vague working instructions. | CMO - Patricia CHRO - Tashi CTO - Jason | Explained through the Deming Cycle process diagram. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | No descriptions/explanations of how materials are defined. | Lack of clarity in direction. Vague working instructions. | COO - Merlyn CFO - Dev | Explained through the Deming Cycle process diagram. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | Missing documents. | Lack of clarity in direction. Vague working instructions. | CTO - Jason CRO - Hemanth | Missing documents provided. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | Incorrect scope statement. | Inexperience. | CEO CMO COO CSO CHRO CTO CFO CRO | Scope Statement revision ongoing. | 2024-10-23 | Ongoing | Pending review @ 2-Nov-2024.
2024-10-14 | No SoA defined. | Lack of coordination between C-level staff. |  | SoA currently being worked on. | 2024-10-23 | Ongoing | Pending review @ 2-Nov-2024.
2024-10-14 | No WMMD. |  |  | WMMD provided. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | No risk process. |  |  | Risk process provided. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | No risk appetite. |  |  | Risk appetite provided. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.
2024-10-14 | Missing consequences table. |  |  | Consequences table provided. | 2024-10-23 | Done | Pending review @ 2-Nov-2024.